## Plan
Plan ID | Plan name | Date of export
MHwUAOOIE0mjO0FrtQBI88kACGPa | R26-IT-061 | 2026-10-14

## Consolidated Data
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
N27I3vW8202_tQLtssa24skAENHw | Report monthly status | Monitoring and controlling |  | Not started | Medium |  | WICKRAMARACHCHI T T it22243980 | 2026-10-13 | 2027-09-08 |  |  | false
_W6hQ2qpHkC0Ej0s7s8PUskAMnAB | Prepare and finalize the intervention optimization thesis draft | Executing |  | In progress | Medium | WICKRAMARACHCHI T T it22243980 | WICKRAMARACHCHI T T it22243980 | 2026-08-31 | 2027-10-14 | 2026-09-26 |  | false
w0bWyUSgCUiN0xYhi8cu6MkANxWa | Conduct team performance reviews | Monitoring and controlling |  | Not started | Medium |  | WICKRAMARACHCHI T T it22243980 | 2026-10-13 | 2032-09-08 |  |  | false
nuV5JeMbfE6iXQcqFLu5fckAAv7M | Refine intervention parameters based on simulation findings and feedback | Executing |  | Completed | Medium | WICKRAMARACHCHI T T it22243980 | WICKRAMARACHCHI T T it22243980 | 2026-08-31 | 2030-09-08 | 2026-09-01 |  | false | 2026-10-13 | WICKRAMARACHCHI T T it22243980
nGCvI4De80mkz1kBgH7OoMkAH1Mf | Develop the intervention section of the research website | Executing |  | In progress | Medium | WICKRAMARACHCHI T T it22243980 | WICKRAMARACHCHI T T it22243980 | 2026-08-30 |  | 2026-10-09 |  | false
CH4XJB5kN0KAiBdIik3gLckAG9iw | Write intervention methodology and contribute to research paper submission | Executing |  | Completed | Medium | WICKRAMARACHCHI T T it22243980 | WICKRAMARACHCHI T T it22243980 | 2026-08-31 | 2026-08-07 | 2026-08-01 |  | false | 2026-08-31 | WICKRAMARACHCHI T T it22243980
nnu3UIaMwkeZEwp0d2Kwf8kAC61h | Configure Supabase Integration | Executing |  | Completed | Medium | WICKRAMARACHCHI T T it22243980 | WICKRAMARACHCHI T T it22243980 | 2026-08-31 | 2026-07-30 | 2026-07-23 |  | false | 2026-08-31 | WICKRAMARACHCHI T T it22243980
CSU38b3BXEylbJtUYLkS_8kAP2SL | Design the reward function and intervention simulation environment | Executing |  | Completed | Medium | WICKRAMARACHCHI T T it22243980 | WICKRAMARACHCHI T T it22243980 | 2026-08-31 | 2026-07-07 | 2026-07-29 |  | false | 2026-08-31 | WICKRAMARACHCHI T T it22243980
9YG8EXreYECVhI8_AgGOlckABJkd | Prepare PP2 presentation, required documents and intervention demonstration | Executing |  | Completed | Medium | WICKRAMARACHCHI T T it22243980 | WICKRAMARACHCHI T T it22243980 | 2026-08-31 | 2026-08-31 | 2026-08-13 |  | false | 2026-08-31 | WICKRAMARACHCHI T T it22243980
-YwOEllgF0SZQJUrrgvViMkAGvkb | Run intervention simulations and compare policy outputs | Executing |  | Completed | Medium | WICKRAMARACHCHI T T it22243980 | WICKRAMARACHCHI T T it22243980 | 2026-08-31 | 2026-07-23 | 2026-07-16 |  | false | 2026-08-31 | WICKRAMARACHCHI T T it22243980
eI8Mne1FtkmbTb2zavWFickADkRU | Develop resource constraints for intervention selection | Executing |  | Completed | Medium | WICKRAMARACHCHI T T it22243980 | WICKRAMARACHCHI T T it22243980 | 2026-08-31 | 2026-07-11 | 2026-07-01 |  | false | 2026-08-31 | WICKRAMARACHCHI T T it22243980
DPEmN-e0VEGoDinP2s9JfckAG7YC | Define MOH-area risk states and intervention action categories | Executing |  | Completed | Medium | WICKRAMARACHCHI T T it22243980 | WICKRAMARACHCHI T T it22243980 | 2026-08-31 | 2026-07-15 | 2026-06-17 |  | false | 2026-08-31 | WICKRAMARACHCHI T T it22243980
c-zhLm1L1U-tkzo_-KhMwckANz1k | Prepare PP1 presentation, supporting documents and intervention demonstration | Executing |  | Completed | Medium | WICKRAMARACHCHI T T it22243980 | WICKRAMARACHCHI T T it22243980 | 2026-08-31 | 2026-07-28 | 2026-06-10 |  | false | 2026-08-31 | WICKRAMARACHCHI T T it22243980
NfFhqi3X-k6Ui6mUqILIDMkAHC7b | Write XAI methodology and discussion and contribute to research paper submission | Executing |  | Completed | Important | HETTIARACHCHI A T it22165848 | HETTIARACHCHI A T it22165848 | 2026-10-13 | 2026-07-28 | 2026-07-15 |  | false | 2026-10-13 | HETTIARACHCHI A T it22165848
Sgl6gSSYhkO0BU6EOjzySskAArXX | Develop readable summaries of prediction explanations | Executing |  | Completed | Medium | HETTIARACHCHI A T it22165848 | HETTIARACHCHI A T it22165848 | 2026-10-13 | 2026-07-07 | 2026-07-02 |  | false | 2026-10-13 | HETTIARACHCHI A T it22165848
IF11wpp7jUimFfxtAp3s38kAOSMe | Generate local explanations for selected prediction cases | Executing |  | Completed | Medium | HETTIARACHCHI A T it22165848 | HETTIARACHCHI A T it22165848 | 2026-10-13 | 2026-06-30 | 2026-06-24 |  | false | 2026-10-13 | HETTIARACHCHI A T it22165848
-HHmJ1cYjEuq-Wjvlc2CFMkAFtx0 | Generate global feature importance plots | Monitoring and controlling |  | Completed | Medium | HETTIARACHCHI A T it22165848 | HETTIARACHCHI A T it22165848 | 2026-10-13 | 2026-08-03 | 2026-10-14 |  | false | 2026-10-13 | HETTIARACHCHI A T it22165848
eSEixc6omU60AKR6CsKm_ckAGqQt | Configure the SHAP explainer for the prediction model | Executing |  | Completed | Medium | HETTIARACHCHI A T it22165848 | HETTIARACHCHI A T it22165848 | 2026-10-13 | 2026-05-16 | 2026-05-13 |  | false | 2026-10-13 | HETTIARACHCHI A T it22165848
k8DtCXHLM0qE2y6KU20hM8kAA325 | Prepare PP1 presentation, supporting documents and XAI demonstration | Executing |  | Completed | Important | HETTIARACHCHI A T it22165848 | HETTIARACHCHI A T it22165848 | 2026-10-13 | 2026-05-02 | 2026-05-01 |  | false | 2026-10-13 | HETTIARACHCHI A T it22165848
xc0Ki4F28kSHjMEVjXxfcskAICeo | Prepare PP2 presentation, required documents and XAI demonstration | Executing |  | Completed | Medium | HETTIARACHCHI A T it22165848 | WICKRAMARACHCHI T T it22243980 | 2026-10-13 | 2026-08-31 | 2026-08-18 |  | false | 2026-10-13 | WICKRAMARACHCHI T T it22243980
n7-qWJECHkihaeHKHDE2T8kAALh8 | Add handling for unavailable explanations and mismatched model features | Executing |  | Completed | Medium | HETTIARACHCHI A T it22165848 | WICKRAMARACHCHI T T it22243980 | 2026-10-13 | 2026-09-17 | 2026-09-02 |  | false | 2026-10-13 | WICKRAMARACHCHI T T it22243980
f_y3EUh6G0aHZ2jyhwW6_skAK9Rt | Prepare and finalize the XAI thesis draft | Executing |  | Completed | Medium | HETTIARACHCHI A T it22165848 | WICKRAMARACHCHI T T it22243980 | 2026-10-13 | 2026-09-29 | 2026-09-24 |  | false | 2026-10-13 | WICKRAMARACHCHI T T it22243980
Wq6MQvcdw0OLW4EKgS59e8kAK8wh | Develop the XAI section of the research website | Executing |  | In progress | Medium | HETTIARACHCHI A T it22165848 | WICKRAMARACHCHI T T it22243980 | 2026-10-13 |  | 2026-10-01 |  | false
CDcJv0kE0USZ6taKDgDyyckACQgu | Prepare PP1 presentation, supporting documents and prediction demonstration | Executing |  | Completed | Medium | KEENAVINNA K A I U it22214034 | WICKRAMARACHCHI T T it22243980 | 2026-10-13 | 2026-05-31 | 2026-05-01 |  | false | 2026-10-13 | WICKRAMARACHCHI T T it22243980
V_ml9U0D9kCn48nBfJiVmskANiPQ | Clean and align weekly dengue and weather datasets | Executing |  | Completed | Medium | KEENAVINNA K A I U it22214034 | WICKRAMARACHCHI T T it22243980 | 2026-10-13 | 2026-06-18 | 2026-06-01 |  | false | 2026-10-13 | WICKRAMARACHCHI T T it22243980
OZPALp4MmEKQOnJ1CAGtV8kAIAsd | Develop lag features and dengue risk labels | Executing |  | Completed | Medium | KEENAVINNA K A I U it22214034 | WICKRAMARACHCHI T T it22243980 | 2026-10-13 | 2026-06-25 | 2026-06-18 |  | false | 2026-10-13 | WICKRAMARACHCHI T T it22243980
bjldtSkXG0SNW-tSWEhJkckAGW9r | Train and tune the Random Forest prediction model | Executing |  | Completed | Medium | KEENAVINNA K A I U it22214034 | WICKRAMARACHCHI T T it22243980 | 2026-10-13 | 2026-07-09 | 2026-06-30 |  | false | 2026-10-13 | WICKRAMARACHCHI T T it22243980
u89FG-6iDU-KT439DEfE-ckAHBWK | Evaluate prediction performance on unseen data | Monitoring and controlling |  | Completed | Medium | KEENAVINNA K A I U it22214034 | WICKRAMARACHCHI T T it22243980 | 2026-10-13 | 2026-07-24 | 2026-07-16 |  | false | 2026-10-13 | WICKRAMARACHCHI T T it22243980
x9dB0l76skqE7_NRtUnFqckAJ7N2 | Write prediction sections and contribute to research paper submission | Executing |  | Completed | Medium | KEENAVINNA K A I U it22214034 | WICKRAMARACHCHI T T it22243980 | 2026-10-13 | 2026-08-20 | 2026-07-30 |  | false | 2026-10-13 | WICKRAMARACHCHI T T it22243980
Z0n1MWE3UU-E0BWjBjVLpMkADLBE | Prepare PP2 presentation, required documents and prediction demonstration | Executing |  | Completed | Medium | KEENAVINNA K A I U it22214034 | WICKRAMARACHCHI T T it22243980 | 2026-10-13 | 2026-08-31 | 2026-08-13 |  | false | 2026-10-13 | WICKRAMARACHCHI T T it22243980
TjpRKyKtrUOm38mK6NfKjMkAMpvh | Refine prediction input validation and missing-data handling | Executing |  | Completed | Medium | KEENAVINNA K A I U it22214034 | WICKRAMARACHCHI T T it22243980 | 2026-10-13 | 2026-09-08 | 2026-09-01 |  | false | 2026-10-13 | WICKRAMARACHCHI T T it22243980
SHC7CdpSh0qkI88tgRBE5skAFibN | Prepare and finalize the prediction thesis draft | Executing |  | In progress | Medium | KEENAVINNA K A I U it22214034 | WICKRAMARACHCHI T T it22243980 | 2026-10-13 |  | 2026-09-23 |  | false
irB5qqE6d0qABtroQ5e53skABy0G | Develop the prediction section of the research website | Executing |  | In progress | Medium | KEENAVINNA K A I U it22214034 | WICKRAMARACHCHI T T it22243980 | 2026-10-13 |  | 2026-10-01 |  | false
7WqAi4zEx0ezTf_CwKt3mckAH14n | Prepare PP1 presentation, supporting documents and component demonstration | Executing |  | Completed | Medium | ADITHYA A A H it22281982 | WICKRAMARACHCHI T T it22243980 | 2026-10-13 | 2026-05-31 | 2026-05-14 |  | false | 2026-10-13 | WICKRAMARACHCHI T T it22243980
QiMRbGidC0qFBLiSgH__cMkACvHs | Prepare and annotate PHI inspection image datasets | Executing |  | Completed | Medium | ADITHYA A A H it22281982 | WICKRAMARACHCHI T T it22243980 | 2026-10-13 | 2026-06-18 | 2026-06-04 |  | false | 2026-10-13 | WICKRAMARACHCHI T T it22243980
Auo-qF7I_0etblKwTKA9KckAP9AC | Develop the image-based inspection detection prototype | Executing |  | Completed | Medium | ADITHYA A A H it22281982 | WICKRAMARACHCHI T T it22243980 | 2026-10-13 | 2026-06-23 | 2026-06-18 |  | false | 2026-10-13 | WICKRAMARACHCHI T T it22243980
3mufLIeraU6Tyq5Ju2fdKMkAEpV5 | Implement English, Sinhala and Singlish text preprocessing | Executing |  | Completed | Medium | ADITHYA A A H it22281982 | WICKRAMARACHCHI T T it22243980 | 2026-10-13 | 2026-07-08 | 2026-07-30 |  | false | 2026-10-13 | WICKRAMARACHCHI T T it22243980
JO6nJa3bnUSmFOoPCFaGJ8kANoSZ | Develop dengue context and misinformation classification modules | Executing |  | Completed | Medium | ADITHYA A A H it22281982 | WICKRAMARACHCHI T T it22243980 | 2026-10-13 | 2026-07-31 | 2026-07-15 |  | false | 2026-10-13 | WICKRAMARACHCHI T T it22243980
N3aV4WydNk2z_fSMeZItiskAGfJK | Write inspection and multilingual sections and contribute to research paper submission | Executing |  | Completed | Medium | ADITHYA A A H it22281982 | WICKRAMARACHCHI T T it22243980 | 2026-10-13 | 2026-08-04 | 2026-07-31 |  | false | 2026-10-13 | WICKRAMARACHCHI T T it22243980
FAQlRHRd20WHPP-_tYf2KMkAJ1LA | Prepare PP2 presentation, required documents and component demonstration | Executing |  | Completed | Medium | ADITHYA A A H it22281982 | WICKRAMARACHCHI T T it22243980 | 2026-10-13 | 2026-10-31 | 2026-08-05 |  | false | 2026-10-13 | WICKRAMARACHCHI T T it22243980
6OoKakC_0k68xXszwaZ-gskAH0GR | Improve evidence retrieval and structured multilingual responses | Executing |  | Completed | Medium | ADITHYA A A H it22281982 | WICKRAMARACHCHI T T it22243980 | 2026-10-13 | 2026-09-16 | 2026-09-01 |  | false | 2026-10-13 | WICKRAMARACHCHI T T it22243980
5Prd4HJjwkqvt-bwSoLzCskAHPoH | Prepare and finalize the inspection and multilingual thesis draft | Executing |  | In progress | Medium | ADITHYA A A H it22281982 | WICKRAMARACHCHI T T it22243980 | 2026-10-13 |  | 2026-09-17 |  | false
01AcidSU70KmTnSXEnEHsckAJ0Ik | Develop the inspection and multilingual section of the research website | Executing |  | In progress | Medium | ADITHYA A A H it22281982 | WICKRAMARACHCHI T T it22243980 | 2026-10-13 |  | 2026-09-30 |  | false

## Tasks
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
N27I3vW8202_tQLtssa24skAENHw | Report monthly status | Bsncvi9hW0awajxArmA_5ckAPSs- |  | Not started | Medium |  | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 2026-10-13 | 2027-09-08 |  |  | false
_W6hQ2qpHkC0Ej0s7s8PUskAMnAB | Prepare and finalize the intervention optimization thesis draft | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | In progress | Medium | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 2026-08-31 | 2027-10-14 | 2026-09-26 |  | false
w0bWyUSgCUiN0xYhi8cu6MkANxWa | Conduct team performance reviews | Bsncvi9hW0awajxArmA_5ckAPSs- |  | Not started | Medium |  | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 2026-10-13 | 2032-09-08 |  |  | false
nuV5JeMbfE6iXQcqFLu5fckAAv7M | Refine intervention parameters based on simulation findings and feedback | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | Completed | Medium | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 2026-08-31 | 2030-09-08 | 2026-09-01 |  | false | 2026-10-13 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6
nGCvI4De80mkz1kBgH7OoMkAH1Mf | Develop the intervention section of the research website | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | In progress | Medium | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 2026-08-30 |  | 2026-10-09 |  | false
CH4XJB5kN0KAiBdIik3gLckAG9iw | Write intervention methodology and contribute to research paper submission | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | Completed | Medium | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 2026-08-31 | 2026-08-07 | 2026-08-01 |  | false | 2026-08-31 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6
nnu3UIaMwkeZEwp0d2Kwf8kAC61h | Configure Supabase Integration | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | Completed | Medium | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 2026-08-31 | 2026-07-30 | 2026-07-23 |  | false | 2026-08-31 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6
CSU38b3BXEylbJtUYLkS_8kAP2SL | Design the reward function and intervention simulation environment | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | Completed | Medium | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 2026-08-31 | 2026-07-07 | 2026-07-29 |  | false | 2026-08-31 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6
9YG8EXreYECVhI8_AgGOlckABJkd | Prepare PP2 presentation, required documents and intervention demonstration | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | Completed | Medium | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 2026-08-31 | 2026-08-31 | 2026-08-13 |  | false | 2026-08-31 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6
-YwOEllgF0SZQJUrrgvViMkAGvkb | Run intervention simulations and compare policy outputs | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | Completed | Medium | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 2026-08-31 | 2026-07-23 | 2026-07-16 |  | false | 2026-08-31 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6
eI8Mne1FtkmbTb2zavWFickADkRU | Develop resource constraints for intervention selection | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | Completed | Medium | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 2026-08-31 | 2026-07-11 | 2026-07-01 |  | false | 2026-08-31 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6
DPEmN-e0VEGoDinP2s9JfckAG7YC | Define MOH-area risk states and intervention action categories | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | Completed | Medium | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 2026-08-31 | 2026-07-15 | 2026-06-17 |  | false | 2026-08-31 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6
c-zhLm1L1U-tkzo_-KhMwckANz1k | Prepare PP1 presentation, supporting documents and intervention demonstration | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | Completed | Medium | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 2026-08-31 | 2026-07-28 | 2026-06-10 |  | false | 2026-08-31 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6
NfFhqi3X-k6Ui6mUqILIDMkAHC7b | Write XAI methodology and discussion and contribute to research paper submission | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | Completed | Important | d629c39e-52df-4b21-afea-a93f089d5e2f | d629c39e-52df-4b21-afea-a93f089d5e2f | 2026-10-13 | 2026-07-28 | 2026-07-15 |  | false | 2026-10-13 | d629c39e-52df-4b21-afea-a93f089d5e2f
Sgl6gSSYhkO0BU6EOjzySskAArXX | Develop readable summaries of prediction explanations | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | Completed | Medium | d629c39e-52df-4b21-afea-a93f089d5e2f | d629c39e-52df-4b21-afea-a93f089d5e2f | 2026-10-13 | 2026-07-07 | 2026-07-02 |  | false | 2026-10-13 | d629c39e-52df-4b21-afea-a93f089d5e2f
IF11wpp7jUimFfxtAp3s38kAOSMe | Generate local explanations for selected prediction cases | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | Completed | Medium | d629c39e-52df-4b21-afea-a93f089d5e2f | d629c39e-52df-4b21-afea-a93f089d5e2f | 2026-10-13 | 2026-06-30 | 2026-06-24 |  | false | 2026-10-13 | d629c39e-52df-4b21-afea-a93f089d5e2f
-HHmJ1cYjEuq-Wjvlc2CFMkAFtx0 | Generate global feature importance plots | Bsncvi9hW0awajxArmA_5ckAPSs- |  | Completed | Medium | d629c39e-52df-4b21-afea-a93f089d5e2f | d629c39e-52df-4b21-afea-a93f089d5e2f | 2026-10-13 | 2026-08-03 | 2026-10-14 |  | false | 2026-10-13 | d629c39e-52df-4b21-afea-a93f089d5e2f
eSEixc6omU60AKR6CsKm_ckAGqQt | Configure the SHAP explainer for the prediction model | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | Completed | Medium | d629c39e-52df-4b21-afea-a93f089d5e2f | d629c39e-52df-4b21-afea-a93f089d5e2f | 2026-10-13 | 2026-05-16 | 2026-05-13 |  | false | 2026-10-13 | d629c39e-52df-4b21-afea-a93f089d5e2f
k8DtCXHLM0qE2y6KU20hM8kAA325 | Prepare PP1 presentation, supporting documents and XAI demonstration | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | Completed | Important | d629c39e-52df-4b21-afea-a93f089d5e2f | d629c39e-52df-4b21-afea-a93f089d5e2f | 2026-10-13 | 2026-05-02 | 2026-05-01 |  | false | 2026-10-13 | d629c39e-52df-4b21-afea-a93f089d5e2f
xc0Ki4F28kSHjMEVjXxfcskAICeo | Prepare PP2 presentation, required documents and XAI demonstration | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | Completed | Medium | d629c39e-52df-4b21-afea-a93f089d5e2f | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 2026-10-13 | 2026-08-31 | 2026-08-18 |  | false | 2026-10-13 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6
n7-qWJECHkihaeHKHDE2T8kAALh8 | Add handling for unavailable explanations and mismatched model features | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | Completed | Medium | d629c39e-52df-4b21-afea-a93f089d5e2f | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 2026-10-13 | 2026-09-17 | 2026-09-02 |  | false | 2026-10-13 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6
f_y3EUh6G0aHZ2jyhwW6_skAK9Rt | Prepare and finalize the XAI thesis draft | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | Completed | Medium | d629c39e-52df-4b21-afea-a93f089d5e2f | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 2026-10-13 | 2026-09-29 | 2026-09-24 |  | false | 2026-10-13 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6
Wq6MQvcdw0OLW4EKgS59e8kAK8wh | Develop the XAI section of the research website | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | In progress | Medium | d629c39e-52df-4b21-afea-a93f089d5e2f | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 2026-10-13 |  | 2026-10-01 |  | false
CDcJv0kE0USZ6taKDgDyyckACQgu | Prepare PP1 presentation, supporting documents and prediction demonstration | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | Completed | Medium | faf2da6a-90b4-4b79-b0d5-81318499310f | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 2026-10-13 | 2026-05-31 | 2026-05-01 |  | false | 2026-10-13 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6
V_ml9U0D9kCn48nBfJiVmskANiPQ | Clean and align weekly dengue and weather datasets | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | Completed | Medium | faf2da6a-90b4-4b79-b0d5-81318499310f | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 2026-10-13 | 2026-06-18 | 2026-06-01 |  | false | 2026-10-13 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6
OZPALp4MmEKQOnJ1CAGtV8kAIAsd | Develop lag features and dengue risk labels | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | Completed | Medium | faf2da6a-90b4-4b79-b0d5-81318499310f | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 2026-10-13 | 2026-06-25 | 2026-06-18 |  | false | 2026-10-13 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6
bjldtSkXG0SNW-tSWEhJkckAGW9r | Train and tune the Random Forest prediction model | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | Completed | Medium | faf2da6a-90b4-4b79-b0d5-81318499310f | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 2026-10-13 | 2026-07-09 | 2026-06-30 |  | false | 2026-10-13 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6
u89FG-6iDU-KT439DEfE-ckAHBWK | Evaluate prediction performance on unseen data | Bsncvi9hW0awajxArmA_5ckAPSs- |  | Completed | Medium | faf2da6a-90b4-4b79-b0d5-81318499310f | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 2026-10-13 | 2026-07-24 | 2026-07-16 |  | false | 2026-10-13 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6
x9dB0l76skqE7_NRtUnFqckAJ7N2 | Write prediction sections and contribute to research paper submission | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | Completed | Medium | faf2da6a-90b4-4b79-b0d5-81318499310f | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 2026-10-13 | 2026-08-20 | 2026-07-30 |  | false | 2026-10-13 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6
Z0n1MWE3UU-E0BWjBjVLpMkADLBE | Prepare PP2 presentation, required documents and prediction demonstration | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | Completed | Medium | faf2da6a-90b4-4b79-b0d5-81318499310f | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 2026-10-13 | 2026-08-31 | 2026-08-13 |  | false | 2026-10-13 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6
TjpRKyKtrUOm38mK6NfKjMkAMpvh | Refine prediction input validation and missing-data handling | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | Completed | Medium | faf2da6a-90b4-4b79-b0d5-81318499310f | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 2026-10-13 | 2026-09-08 | 2026-09-01 |  | false | 2026-10-13 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6
SHC7CdpSh0qkI88tgRBE5skAFibN | Prepare and finalize the prediction thesis draft | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | In progress | Medium | faf2da6a-90b4-4b79-b0d5-81318499310f | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 2026-10-13 |  | 2026-09-23 |  | false
irB5qqE6d0qABtroQ5e53skABy0G | Develop the prediction section of the research website | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | In progress | Medium | faf2da6a-90b4-4b79-b0d5-81318499310f | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 2026-10-13 |  | 2026-10-01 |  | false
7WqAi4zEx0ezTf_CwKt3mckAH14n | Prepare PP1 presentation, supporting documents and component demonstration | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | Completed | Medium | fb79dea6-4c1d-46ee-a52a-c9d6851be729 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 2026-10-13 | 2026-05-31 | 2026-05-14 |  | false | 2026-10-13 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6
QiMRbGidC0qFBLiSgH__cMkACvHs | Prepare and annotate PHI inspection image datasets | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | Completed | Medium | fb79dea6-4c1d-46ee-a52a-c9d6851be729 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 2026-10-13 | 2026-06-18 | 2026-06-04 |  | false | 2026-10-13 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6
Auo-qF7I_0etblKwTKA9KckAP9AC | Develop the image-based inspection detection prototype | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | Completed | Medium | fb79dea6-4c1d-46ee-a52a-c9d6851be729 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 2026-10-13 | 2026-06-23 | 2026-06-18 |  | false | 2026-10-13 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6
3mufLIeraU6Tyq5Ju2fdKMkAEpV5 | Implement English, Sinhala and Singlish text preprocessing | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | Completed | Medium | fb79dea6-4c1d-46ee-a52a-c9d6851be729 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 2026-10-13 | 2026-07-08 | 2026-07-30 |  | false | 2026-10-13 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6
JO6nJa3bnUSmFOoPCFaGJ8kANoSZ | Develop dengue context and misinformation classification modules | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | Completed | Medium | fb79dea6-4c1d-46ee-a52a-c9d6851be729 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 2026-10-13 | 2026-07-31 | 2026-07-15 |  | false | 2026-10-13 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6
N3aV4WydNk2z_fSMeZItiskAGfJK | Write inspection and multilingual sections and contribute to research paper submission | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | Completed | Medium | fb79dea6-4c1d-46ee-a52a-c9d6851be729 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 2026-10-13 | 2026-08-04 | 2026-07-31 |  | false | 2026-10-13 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6
FAQlRHRd20WHPP-_tYf2KMkAJ1LA | Prepare PP2 presentation, required documents and component demonstration | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | Completed | Medium | fb79dea6-4c1d-46ee-a52a-c9d6851be729 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 2026-10-13 | 2026-10-31 | 2026-08-05 |  | false | 2026-10-13 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6
6OoKakC_0k68xXszwaZ-gskAH0GR | Improve evidence retrieval and structured multilingual responses | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | Completed | Medium | fb79dea6-4c1d-46ee-a52a-c9d6851be729 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 2026-10-13 | 2026-09-16 | 2026-09-01 |  | false | 2026-10-13 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6
5Prd4HJjwkqvt-bwSoLzCskAHPoH | Prepare and finalize the inspection and multilingual thesis draft | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | In progress | Medium | fb79dea6-4c1d-46ee-a52a-c9d6851be729 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 2026-10-13 |  | 2026-09-17 |  | false
01AcidSU70KmTnSXEnEHsckAJ0Ik | Develop the inspection and multilingual section of the research website | uqghW1B-cEmVafjIR4YsX8kAGW4S |  | In progress | Medium | fb79dea6-4c1d-46ee-a52a-c9d6851be729 | 73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | 2026-10-13 |  | 2026-09-30 |  | false

## Goals
Goal ID | Goal name | Status | Priority | Start date | Finish date | Connected tasks | Notes

## Buckets
Bucket ID | Bucket Name
-JW3WQi94EW2SL0ENXEXaskAMS-X | Initiating
o9m-882Ok0mWUC9vwuhIwskAB0es | Planning
uqghW1B-cEmVafjIR4YsX8kAGW4S | Executing
Bsncvi9hW0awajxArmA_5ckAPSs- | Monitoring and controlling
oeFXra3TUU63zkU3BpNWAMkAPDly | Closing

## Users
User ID | User Name | Email
73f60532-2d9d-4fea-934d-2ebea1d3f4e6 | WICKRAMARACHCHI T T it22243980 | it22243980@my.sliit.lk
d629c39e-52df-4b21-afea-a93f089d5e2f | HETTIARACHCHI A T it22165848 | it22165848@my.sliit.lk
faf2da6a-90b4-4b79-b0d5-81318499310f | KEENAVINNA K A I U it22214034 | it22214034@my.sliit.lk
fb79dea6-4c1d-46ee-a52a-c9d6851be729 | ADITHYA A A H it22281982 | it22281982@my.sliit.lk